## T9
|  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  | 18 |  |  |  | 19 |  |  |  | 20 |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  | 24 |  |  |  | 25 |  |  |  | 26 |  |  |  | 27 |  |  |  | 28 |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32 |  |  |  | 33 |  |  |  | 34
|  | CONTRACTOR | CATEGORY | 201 | 202 | 203 | 204 | 301 | 302 | 303 | 304 | 401 | 402 | 403 | 404 | 501 | 502 | 503 | 504 | 601 | 602 | 603 | 604 | 701 | 702 | 703 | 704 | 801 | 802 | 803 | 804 | 901 | 902 | 903 | 904 | 1001 | 1002 | 1003 | 1004 | 1101 | 1102 | 1103 | 1104 | 1201 | 1202 | 1203 | 1204 | 1301 | 1302 | 1303 | 1304 | 1401 | 1402 | 1403 | 1404 | 1501 | 1502 | 1503 | 1504 | 1601 | 1602 | 1603 | 1604 | 1701 | 1702 | 1703 | 1704 | 1801 | 1802 | 1803 | 1804 | 1901 | 1902 | 1903 | 1904 | 2001 | 2002 | 2003 | 2004 | 2101 | 2102 | 2103 | 2104 | 2201 | 2202 | 2203 | 2204 | 2301 | 2302 | 2303 | 2304 | 2401 | 2402 | 2403 | 2404 | 2501 | 2502 | 2503 | 2504 | 2601 | 2602 | 2603 | 2604 | 2701 | 2702 | 2703 | 2704 | 2801 | 2802 | 2803 | 2804 | 2901 | 2902 | 2903 | 2904 | 3001 | 3002 | 3003 | 3004 | 3101 | 3102 | 3103 | 3104 | 3201 | 3202 | 3203 | 3204 | 3301 | 3302 | 3303 | 3304 | 3401 | 3402 | 3403 | 3404
APARTEMENTS (PRE FINAL STAGE ) | Blockwork | SSC | bar: 2 201 to 34 3404
| Wall Conduiting & Switch Boxing | SSC | bar: 2 201 to 34 3404
| Plb. Works (UPVC Drainage Works ) | AGS | bar: 2 201 to 34 3404
| Waterproofing/Bore packing in Toilet/Kit. | Star Merc. | bar: 2 201 to 34 3404
| Ledge Wall Brickwork | Star Merc. | bar: 2 201 to 34 3404
| Rough Cement Plastering works Toilet/Kit. | Star Merc. | bar: 2 201 to 34 3404
| CPVC Piping & Testing Works | AGS | bar: 2 201 to 34 3404
| IPS Flooring | Star Merc. | bar: 2 201 to 34 3404
| Fire Fighting piping & Testing works | Shannon | bar: 2 201 to 34 3404
| Gypsum Plastering works | Star Merc. | bar: 2 201 to 34 3404
| Toilet Tiling Works-Floor & Dado | Star Merc. | bar: 2 201 to 34 3404
| Kitchen Tiling Works-Floor & Dado | Star Merc. | bar: 2 201 to 34 3404
| Stone Flooring Works | Star Merc. | bar: 2 201 to 34 3404
| Balcony MS Louvers Fixing | -
| FF Boxing | Star Merc. | bar: 3 301 to 15 1504
| Balcony Tile Flooring | Star Merc. | bar: 2 201 to 34 3404
| Internal Paint - Base work | Star Merc. | bar: 2 201 to 12 1204
| Pre Hung-Main Door Fixing | Shreeji
| Toilet Cill | Star Merc.
| Al. Doors & Windows [FRAME] | Alpro | bar: 2 201 to 34 3404
| Al. Doors & Windows [SHUTTER] | Alpro | bar: 4 401 to 6 604
| Glass Railing Works | Vertical F. | bar: 3 301 to 3 304; 4 402 to 5 504; 6 602 to 7 704; 8 802 to 9 904; 10 1002 to 11 1104; 12 1203 to 13 1304; 14 1403; 15 1501 to 15 1504; 16 1603
| Balcony upstand Granite Fixing | Star Merc.
| Electrical Wiring | TripleA
| Fire Alarm Wiring | TripleA
| Door/window & Ele. Junction repair with POP | Star Merc.
| Toilet Counter works | Star Merc. | bar: 4 401 to 12 1204
| Internal Door Fixing | Shreeji
| Internal Paint - Pre-final | Star Merc.
| Rainwater Drain Fixing | AGS
HANDING OVER STAGE | Modular Kitchent works | Dynasty
| CP & Chinaware Installtion | AGS
| AC Installation | -
| Energy Meter | TripleA
| Final Paint & Touch up works | Star Merc.
| Woodne Floorinf Fixing | -
| Light Fixtures & Switch Socker Fixing | TripleA
| Grid Ceiling in Toilet | Star Merc. | bar: 2 201 to 2 204
COMMON AREA | Lift Shafts Brickwork | TKE | bar: 2 201 to 34 3404
| Lift Shaft Plastering Works | TKE | bar: 2 201 to 34 3404
| FF Fighting piping Works | Shannon | bar: 2 201 to 34 3404
| Common Area Elec. Wiring | TripleA | bar: 2 201 to 34 3404
| Fire Alarm Wiring | Niveshan | bar: 2 201 to 34 3404
| Fire Door | Navair | bar: 2 201 to 34 3404
| FF Boxing Works | Star Merc. | bar: 4 401 to 12 1204
| Fire Riser Inst./Testing | Shannon | bar: 2 201 to 34 3404
| Plumbing Inst./Testing | AGS | bar: 2 201 to 34 3404
| Lobby Internal Plaster | Star Merc. | bar: 2 201 to 22 2204; 27 2701 to 28 2804
| Tile Flooring | Star Merc. | bar: 2 201 to 19 1904; 25 2501 to 25 2504
| Lift Installation & Door Frame Fixing | TKE | bar: 2 201 to 34 3404
| Lift Cladding | Star Merc. | bar: 2 201 to 34 3404
| Putty & Base paint works | Star Merc.
| Electrical Shaft Door | Navair | bar: 2 201 to 34 3404
| Electrical Cable Tray | TripleA | bar: 2 201 to 34 3404
| Electrical Cable Laying | TripleA | bar: 2 201 to 34 3404
| Fire Alarm | Niveshan
| FHC Accessories | Shannon | bar: 2 201 to 2 204
| POP repair & Pre Final stage upto Primer | Star Merc.
| Staircase Plastering Works | Star Merc.
| MAIN Stair-case Stone Fixing | Star Merc. | bar: 3 301 to 8 804; 32 3201 to 34 3404
| FIRE Stair-case Stone Fixing | Star Merc. | bar: 2 201 to 34 3404
| Main Staircase Railing | Star Merc.
| Fire Staircase Railing | Star Merc. | bar: 8 801 to 25 2504
| Pre Final Paint Staircase ( up to primer) | Star Merc.
| Railing Enamel Paint | Star Merc.
External Façade & painting | Façade/External Dead walls Primer | Amaze |  | 2 201: 90%
| Façade/External Dead walls Texture | Amaze |  | 2 201: 45%
| External Dead Walls 1st Coat Paint | Amaze |  | 2 201: 45%
| External Dead Walls 2nd Coat Paint | Amaze | bar: 2 201
| Balcony Ceiling Paint | -
| Balcony Texture Paint | -
| Balcony 1st Coat Paint | -
| Expansion Gap covering | -

## T10
|  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  | 18 |  |  |  | 19 |  |  |  | 20 |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  | 24 |  |  |  | 25 |  |  |  | 26 |  |  |  | 27 |  |  |  | 28 |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32 |  |  |  | 33 |  |  |  | 34
|  | CONTRACTOR | CATEGORY | 201 | 202 | 203 | 204 | 301 | 302 | 303 | 304 | 401 | 402 | 403 | 404 | 501 | 502 | 503 | 504 | 601 | 602 | 603 | 604 | 701 | 702 | 703 | 704 | 801 | 802 | 803 | 804 | 901 | 902 | 903 | 904 | 1001 | 1002 | 1003 | 1004 | 1101 | 1102 | 1103 | 1104 | 1201 | 1202 | 1203 | 1204 | 1301 | 1302 | 1303 | 1304 | 1401 | 1402 | 1403 | 1404 | 1501 | 1502 | 1503 | 1504 | 1601 | 1602 | 1603 | 1604 | 1701 | 1702 | 1703 | 1704 | 1801 | 1802 | 1803 | 1804 | 1901 | 1902 | 1903 | 1904 | 2001 | 2002 | 2003 | 2004 | 2101 | 2102 | 2103 | 2104 | 2201 | 2202 | 2203 | 2204 | 2301 | 2302 | 2303 | 2304 | 2401 | 2402 | 2403 | 2404 | 2501 | 2502 | 2503 | 2504 | 2601 | 2602 | 2603 | 2604 | 2701 | 2702 | 2703 | 2704 | 2801 | 2802 | 2803 | 2804 | 2901 | 2902 | 2903 | 2904 | 3001 | 3002 | 3003 | 3004 | 3101 | 3102 | 3103 | 3104 | 3201 | 3202 | 3203 | 3204 | 3301 | 3302 | 3303 | 3304 | 3401 | 3402 | 3403 | 3404
APARTEMENTS (PRE FINAL STAGE ) | Blockwork | SSC | bar: 2 201 to 34 3404
| Wall Conduiting & Switch Boxing | SSC | bar: 2 201 to 34 3404
| Plb. Works (UPVC Drainage Works ) | AGS | bar: 2 201 to 34 3404
| Waterproofing/Bore packing in Toilet/Kit. | Star Merc. | bar: 2 201 to 34 3404
| Ledge Wall Brickwork | Star Merc. | bar: 2 201 to 34 3404
| Rough Cement Plastering works Toilet/Kit. | Star Merc. | bar: 2 201 to 34 3404
| CPVC Piping & Testing Works | AGS | bar: 2 201 to 34 3404
| IPS Flooring | Star Merc. | bar: 2 201 to 34 3404
| Fire Fighting piping & Testing works | Shannon | bar: 2 201 to 34 3404
| Gypsum Plastering works | Star Merc. | bar: 2 201 to 34 3404
| Toilet Tiling Works-Floor & Dado | Star Merc. | bar: 2 201 to 34 3404
| Kitchen Tiling Works-Floor & Dado | Star Merc. | bar: 2 201 to 34 3404
| Stone Flooring Works | Star Merc. | bar: 2 201 to 25 2504; 29 2901 to 29 2904; 30 3002; 32 3201 to 34 3404
| Balcony MS Louvers Fixing | -
| FF Boxing (Framing) | Star Merc. | bar: 2 201 to 24 2404
| Balcony Tile Flooring | Star Merc. | bar: 2 201 to 34 3404
| Internal Paint - Base work | Star Merc. | bar: 2 201 to 18 1802
| Pre Hung-Main Door Fixing | Shreeji
| Toilet Cill | Star Merc. | bar: 2 201 to 32 3204
| Al. Doors & Windows [FRAME] | Alpro | bar: 2 201 to 26 2604
| Al. Doors & Windows [SHUTTER] | Alpro | bar: 2 201 to 10 1004
| Glass Railing Works | Vertical F. | bar: 2 201 to 2 202
| Balcony upstand Granite Fixing | Star Merc.
| Electrical Wiring | TripleA
| Fire Alarm Wiring | TripleA | bar: 2 201 to 34 3404
| Door/window & Ele. Junction repair with POP | Star Merc. | bar: 2 201 to 13 1304
| Toilet Counter works | Star Merc. | bar: 2 201 to 20 2004
| Internal Door Fixing | Shreeji | bar: 2 201 to 2 204
| Internal Paint - Pre-final | Star Merc.
| Rainwater Drain Fixing | AGS
HANDING OVER STAGE | Modular Kitchent works | Dynasty
| CP & Chinaware Installtion | AGS
| AC Installation | -
| Energy Meter | TripleA
| Final Paint & Touch up works | Star Merc.
| Woodne Floorinf Fixing | -
| Light Fixtures & Switch Socker Fixing | TripleA
| Grid Ceiling in Toilet | Star Merc.
COMMON AREA | Lift Shafts Brickwork | TKE | bar: 2 201 to 34 3404
| Lift Shaft Plastering Works | TKE | bar: 2 201 to 34 3404
| FF Fighting piping Works | Shannon | bar: 2 201 to 34 3404
| Common Area Elec. Wiring | TripleA
| Fire Alarm Wiring | Niveshan | bar: 2 201 to 34 3404
| Fire Door | Navair | bar: 4 401 to 25 2504
| FF Boxing Works | Star Merc.
| Fire Riser Inst./Testing | Shannon | bar: 2 201 to 34 3404
| Plumbing Inst./Testing | AGS
| Lobby Internal Plaster | Star Merc. | bar: 2 201 to 25 2504
| Tile Flooring | Star Merc. | bar: 2 201 to 33 3304
| Lift Installation & Door Frame Fixing | TKE | bar: 2 201 to 34 3404
| Lift Cladding | Star Merc. | bar: 2 201 to 30 3004
| Putty & Base paint works | Star Merc.
| Electrical Shaft Door | Navair | bar: 2 201 to 34 3404
| Electrical Cable Tray | TripleA
| Electrical Cable Laying | TripleA
| Fire Alarm (Wiring) | Niveshan
| FHC Accessories | Shannon
| POP repair & Pre Final stage upto Primer | Star Merc.
| Staircase Plastering Works | Star Merc.
| MAIN Stair-case Stone Fixing | Star Merc. | bar: 2 201 to 34 3404
| FIRE Stair-case Stone Fixing | Star Merc. | bar: 2 201 to 34 3404
| MAIN Staircase Railing | Star Merc. | bar: 2 201 to 3 304
| FIRE Staircase Railing | Star Merc.
| Pre Final Paint Staircase ( up to primer) | Star Merc.
| Railing Enamel Paint | Star Merc.
External Façade & painting | Façade/External Dead walls Primer | Amaze |  | 2 201: 85%
| Façade/External Dead walls Texture | Amaze |  | 2 201: 30%
| External Dead Walls 1st Coat Paint | Amaze |  | 2 201: 30%
| External Dead Walls 2nd Coat Paint | Amaze | bar: 2 201
| Balcony Ceiling Paint | -
| Balcony Texture Paint | -
| Balcony 1st Coat Paint | -
| Expansion Gap covering | -