## T9
|  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  | 18 |  |  |  | 19 |  |  |  | 20 |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  | 24 |  |  |  | 25 |  |  |  | 26 |  |  |  | 27 |  |  |  | 28 |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32 |  |  |  | 33 |  |  |  | 34
|  | 201 | 202 | 203 | 204 | 301 | 302 | 303 | 304 | 401 | 402 | 403 | 404 | 501 | 502 | 503 | 504 | 601 | 602 | 603 | 604 | 701 | 702 | 703 | 704 | 801 | 802 | 803 | 804 | 901 | 902 | 903 | 904 | 1001 | 1002 | 1003 | 1004 | 1101 | 1102 | 1103 | 1104 | 1201 | 1202 | 1203 | 1204 | 1301 | 1302 | 1303 | 1304 | 1401 | 1402 | 1403 | 1404 | 1501 | 1502 | 1503 | 1504 | 1601 | 1602 | 1603 | 1604 | 1701 | 1702 | 1703 | 1704 | 1801 | 1802 | 1803 | 1804 | 1901 | 1902 | 1903 | 1904 | 2001 | 2002 | 2003 | 2004 | 2101 | 2102 | 2103 | 2104 | 2201 | 2202 | 2203 | 2204 | 2301 | 2302 | 2303 | 2304 | 2401 | 2402 | 2403 | 2404 | 2501 | 2502 | 2503 | 2504 | 2601 | 2602 | 2603 | 2604 | 2701 | 2702 | 2703 | 2704 | 2801 | 2802 | 2803 | 2804 | 2901 | 2902 | 2903 | 2904 | 3001 | 3002 | 3003 | 3004 | 3101 | 3102 | 3103 | 3104 | 3201 | 3202 | 3203 | 3204 | 3301 | 3302 | 3303 | 3304 | 3401 | 3402 | 3403 | 3404
APARTEMENTS (PRE FINAL STAGE ) | Blockwork | bar: 2 201 to 34 3404
Wall Conduiting & Switch Boxing | bar: 2 201 to 34 3404
Plb. Works (UPVC Drainage Works ) | bar: 2 201 to 34 3404
Waterproofing/Bore packing in Toilet/Kit. | bar: 2 201 to 34 3404
Ledge Wall Brickwork | bar: 2 201 to 34 3404
Rough Cement Plastering works Toilet/Kit. | bar: 2 201 to 34 3404
CPVC Piping & Testing Works | bar: 2 201 to 34 3404
IPS Flooring | bar: 2 201 to 34 3404
Fire Fighting piping & Testing works | bar: 2 201 to 34 3404
Gypsum Plastering works | bar: 2 201 to 34 3404
Toilet Tiling Works-Floor & Dado | bar: 2 201 to 34 3404
Kitchen Tiling Works-Floor & Dado | bar: 2 201 to 34 3404
Stone Flooring Works | bar: 2 201 to 34 3404
Balcony MS Louvers Fixing
FF Boxing | bar: 3 301 to 15 1504
Balcony Tile Flooring | bar: 2 201 to 34 3404
Internal Paint - Base work | bar: 2 201 to 12 1204
Pre Hung-Main Door Fixing
Al. Doors & Windows [FRAME] | bar: 2 201 to 34 3404
Al. Doors & Windows [SHUTTER] | bar: 4 401 to 6 604
Glass Railing Works | bar: 3 301 to 11 1104
Electrical Wiring
Fire Alarm Wiring
Door/window & Ele. Junction repair with POP
Balcony Railing Enamel Paint
Toilet Counter works | bar: 4 401 to 12 1204
Internal Door Fixing
Internal Paint - Pre-final
HANDING OVER STAGE | Modular Kitchent works
CP & Chinaware Installtion
AC Installation
Energy Meter
Final Paint & Touch up works
Woodne Floorinf Fixing
Light Fixtures & Switch Socker Fixing
Grid Ceiling in Toilet | bar: 2 201 to 2 204
COMMON AREA | Lift Shafts Brickwork
Lift Shaft Plastering Works
FF Fighting piping Works
Ele. Wiring
Fire Alarm Wiring
Fire Door | bar: 2 201 to 34 3404
FF Boxing Works | bar: 4 401 to 12 1204
Fire Riser Inst./Testing
Plumbing Inst./Testing
Lobby Internal Plaster | bar: 2 201 to 22 2204; 27 2701 to 28 2804
Tile Flooring | bar: 2 201 to 19 1904
Lift Installation & Door Frame Fixing
| Lift Cladding | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Putty & Base paint works
Electrical Shaft Door
Electrical Cable Tray
Electrical Cable Laying
Fire Alarm & FHC Accessories
POP repair & Pre Final stage upto Primer
Staircase Plastering Works
MAIN Stair-case Stone Fixing | bar: 3 301 to 8 804; 32 3201 to 34 3404
FIRE Stair-case Stone Fixing | bar: 2 201 to 34 3404
MS Railing in Stair-case
Pre Final Paint Staircase ( up to primer)
Railing Enamel Paint
External Façade & painting | Façade/External Dead walls Primer
Façade/External Dead walls Texture
External Dead Walls 1st Coat Paint
External Dead Walls 2nd Coat Paint
Balcony Ceiling Paint
Balcony Texture Paint
Balcony 1st Coat Paint
Expansion Gap covering

## T10
|  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  | 18 |  |  |  | 19 |  |  |  | 20 |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  | 24 |  |  |  | 25 |  |  |  | 26 |  |  |  | 27 |  |  |  | 28 |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32 |  |  |  | 33 |  |  |  | 34
|  | 201 | 202 | 203 | 204 | 301 | 302 | 303 | 304 | 401 | 402 | 403 | 404 | 501 | 502 | 503 | 504 | 601 | 602 | 603 | 604 | 701 | 702 | 703 | 704 | 801 | 802 | 803 | 804 | 901 | 902 | 903 | 904 | 1001 | 1002 | 1003 | 1004 | 1101 | 1102 | 1103 | 1104 | 1201 | 1202 | 1203 | 1204 | 1301 | 1302 | 1303 | 1304 | 1401 | 1402 | 1403 | 1404 | 1501 | 1502 | 1503 | 1504 | 1601 | 1602 | 1603 | 1604 | 1701 | 1702 | 1703 | 1704 | 1801 | 1802 | 1803 | 1804 | 1901 | 1902 | 1903 | 1904 | 2001 | 2002 | 2003 | 2004 | 2101 | 2102 | 2103 | 2104 | 2201 | 2202 | 2203 | 2204 | 2301 | 2302 | 2303 | 2304 | 2401 | 2402 | 2403 | 2404 | 2501 | 2502 | 2503 | 2504 | 2601 | 2602 | 2603 | 2604 | 2701 | 2702 | 2703 | 2704 | 2801 | 2802 | 2803 | 2804 | 2901 | 2902 | 2903 | 2904 | 3001 | 3002 | 3003 | 3004 | 3101 | 3102 | 3103 | 3104 | 3201 | 3202 | 3203 | 3204 | 3301 | 3302 | 3303 | 3304 | 3401 | 3402 | 3403 | 3404
APARTEMENTS (PRE FINAL STAGE ) | Blockwork | bar: 2 201 to 34 3404
Wall Conduiting & Switch Boxing | bar: 2 201 to 34 3404
Plb. Works (UPVC Drainage Works ) | bar: 2 201 to 34 3404
Waterproofing/Bore packing in Toilet/Kit. | bar: 2 201 to 34 3404
Ledge Wall Brickwork | bar: 2 201 to 34 3404
Rough Cement Plastering works Toilet/Kit. | bar: 2 201 to 34 3404
CPVC Piping & Testing Works | bar: 2 201 to 34 3404
IPS Flooring | bar: 2 201 to 34 3404
Fire Fighting piping & Testing works | bar: 2 201 to 34 3404
Gypsum Plastering works | bar: 2 201 to 34 3404
Toilet Tiling Works-Floor & Dado | bar: 2 201 to 34 3404
Kitchen Tiling Works-Floor & Dado | bar: 2 201 to 34 3404
Stone Flooring Works | bar: 2 201 to 25 2503; 29 2904; 30 3002; 32 3201 to 32 3204; 33 3303 to 34 3404
Balcony MS Louvers Fixing
FF Boxing (Framing) | bar: 2 201 to 24 2404
Balcony Tile Flooring | bar: 2 201 to 34 3404
Internal Paint - Base work | bar: 2 201 to 16 1604; 17 1703 to 18 1802
Pre Hung-Main Door Fixing
Al. Doors & Windows [FRAME] | bar: 2 201 to 26 2604
Al. Doors & Windows [SHUTTER] | bar: 2 201 to 10 1004
Glass Railing Works | bar: 2 201 to 2 202
Electrical Wiring
Fire Alarm Wiring | bar: 2 201 to 34 3404
Door/window & Ele. Junction repair with POP | bar: 2 201 to 34 3404
Balcony Railing Enamel Paint
Toilet Counter works | bar: 2 201 to 20 2004
Internal Door Fixing | bar: 2 201 to 2 204
Internal Paint - Pre-final
HANDING OVER STAGE | Modular Kitchent works
CP & Chinaware Installtion
AC Installation
Energy Meter
Final Paint & Touch up works
Woodne Floorinf Fixing
Light Fixtures & Switch Socker Fixing
Grid Ceiling in Toilet
COMMON AREA | Lift Shafts Brickwork | bar: 2 201 to 34 3404
Lift Shaft Plastering Works | bar: 2 201 to 34 3404
FF Fighting piping Works | bar: 2 201 to 34 3404
Ele. Wiring
Fire Alarm Wiring | bar: 2 201 to 34 3404
Fire Door | bar: 4 401 to 25 2504
FF Boxing Works
Fire Riser Inst./Testing | bar: 2 201 to 34 3404
Plumbing Inst./Testing
Lobby Internal Plaster | bar: 2 201 to 25 2504
Tile Flooring | bar: 2 201 to 34 3404
Lift Installation & Door Frame Fixing | bar: 2 201 to 34 3404
Lift Cladding | bar: 2 201 to 30 3004
Putty & Base paint works
Electrical Shaft Door | bar: 2 201 to 34 3404
Electrical Cable Tray
Electrical Cable Laying
Fire Alarm & FHC Accessories
POP repair & Pre Final stage upto Primer
Staircase Plastering Works
MAIN Stair-case Stone Fixing | bar: 2 201 to 34 3404
FIRE Stair-case Stone Fixing | bar: 2 201 to 34 3404
MS Railing in Stair-case | bar: 2 201 to 3 304
Pre Final Paint Staircase ( up to primer)
Railing Enamel Paint
External Façade & painting | Façade/External Dead walls Primer | 2 201: 85%
| Façade/External Dead walls Texture | 2 201: 30%
| External Dead Walls 1st Coat Paint | 2 201: 30%
External Dead Walls 2nd Coat Paint | bar: 2 201
Balcony Ceiling Paint
Balcony Texture Paint
Balcony 1st Coat Paint
Expansion Gap covering